## Sheet1
| 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
Item | Jan 1 Mar 31 | Apr 1 June 30 | July 1 Sept 30 | Oct 1 Dec 31 | Jan 1 Mar 31 | Apr 1 June 30 | July 1 Sept 30 | Oct 1 Dec 31 | Jan 1 Mar 31 | Apr 1 June 30 | July 1 Sept 30 | Oct 1 Dec 31 | Jan 1 Mar 31 | Apr 1 June 30 | July 1 Sept 30 | Oct 1 Dec 31
Business Plan | >>>>>>>>>>>>>>>>>>>>>>>>>>> |  |  |  | >>>>>>>>>>>
New Name | >>>>> Complete
Market Research | >>>>>>>>>>>>>>>>>>>>>>>>>>
Search for Brewmaster | >>>>>>>>> Completed
Incorporation | >>>> Completed
Open Bank Account/Gov't services | >>>> Completed
Secure Investment | >>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>
Design of Marketing Materials | >>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>>
Update all Forms with new Name | >>> Completed
Board of Directors Forms |  |  |  | >>>>>>>>>>>>>
Apply for EBC Tax Credit | >>>> Completed
Website |  |  |  | >>>>>>>>>>>>>
Bottle and Labels and POS |  |  |  | >>>>>>>>>>>>>
Research and Choose Equipment |  |  | >>>>>>>>>>>>>
Design and Plan brewhouse |  |  |  | >>>>>>>>>>>>
Online Marketing Begins |  |  | >>>>>>>>>>>
Lease Space |  |  | >>>>>>>>>>>>>>
Apply for Business License |  |  |  | >>>>>>>>>>>>
Apply for Manufacturers License |  |  |  | >>>>>>
Apply for Registration Number with BCLDB |  |  |  | >>>>>>>>
Take Possesion of Warehouse |  |  |  |  | >>>>>>
Leasehold Improvements |  |  |  |  | >>>>>>>>>>>>>>>>>>>>>
Procurement of Glasses | [5 empty] | >>>>>>>>>>>>>
Brewing Machinery Ordered |  |  |  |  | >>>>>>>>>>
Conditioning Vessels Ordered |  |  |  |  | >>>>>>>>>>>
POS Material for Establishments | [5 empty] | >>>>>>>>>>>>>>>>>>>>>>
Brewmaster Begins FT Employment | [5 empty] | >>>>>>>>>>>>
Steel Kegs | [5 empty] | >>>>>>>>
Apply for Listing with BCLDB | [5 empty] | >>>>>>>>>
Wooden Kegs | [5 empty] | >>>>>>>>>
Installation of Brewing Equipment | [6 empty] | >>>>>>>>>
Cold Storage created | [6 empty] | >>>>>>>>>
Brewery testing/optimization | [6 empty] | >>>>>>>>>
Begin Marketing Contract Brewing | [6 empty] | >>>>>>>>>>
Maufacturers License Granted | [6 empty] | >>>>>>>
Commercial Production Begins | [6 empty] | >>>>>>>
Exhibits and Booths for TCM | [5 empty] | >>>>>>>>>>>>>
1st Account | [6 empty] | >>>>>>>
10th Account | [7 empty] | >>>>>
25th Account | [7 empty] | >>>>>
Full Time Salesperson joins team | [8 empty] | >>>>>>>>
Sales effort to BCLS | [8 empty] | >>>>>>>>>>>>>
Warehouse Assistant joins team | [8 empty] | >>>>>>>>>>